## Project_Plan
MS# | Milestone | What You Will Do | Days | Duration | Planned_St_Dt | Planned_End_Dt | Status | % Complete | Comments
1 | Setup & Understanding | Create API accounts, set up Google Colab, read about thinking vs instruct models, watch 2–3 YouTube explainers on how LLMs work | Day 1–3 | 3 Days | 2026-03-18 | 2026-03-20 | Completed | 0% | a) qwen/qwen3-32b GPT OSS 120 B b) Open Ai O3 mini --======== c) Llama-3.1 8B Instruct d) Llama-3.3 70B versatile --- > API accounts creation completed > Google Colab set up completed
2 | Learn the Models | Manually chat with each model in the browser (no coding yet); ask the same 10 questions to all 4 models; note differences in style and depth of response | Day 4–7 | 4 Days | 2026-03-21 | 2026-03-24 | Completed | 0%
3 | Build Your Test Script | Write a simple Python script in Colab that sends a question to each model via API and saves the response | Day 8–12 | 5 Days | 2026-03-25 | 2026-03-29 | Completed | 0%
4 | Run Math Task Tests | Send 50 GSM8K questions to all 4 models using your script; record answers, accuracy, and time; fill in your Excel scorecard | Day 13–16 | 4 Days | 2026-03-30 | 2026-04-02 | Completed | 0%
5 | Run Coding Task Tests | Send 25 HumanEval problems to all 4 models; manually check if the code runs; score each response | Day 17–20 | 4 Days | 2026-04-03 | 2026-04-06 | Completed | 0%
6 | Run Q&A Task Tests | Send 50 general knowledge questions; score accuracy and clarity; read reasoning traces from thinking models and summarise observations | Day 21–23 | 3 Days | 2026-04-07 | 2026-04-09 | Completed | 0%
7 | Analysis & Charts | Calculate final accuracy percentages; create bar charts comparing models; write a short summary of which model performed best on each task | Day 24–27 | 4 Days | 2026-04-10 | 2026-04-13 | Completed | 0%
8 | Report & Presentation | Write your final report (2–4 pages); prepare a 10-slide presentation; include your recommendation on when to use each model type | Day 28–30 | 3 Days | 2026-04-14 | 2026-04-16 | In progress | 0%
| Google - Meet Link for Group 1 | https://meet.google.com/edw-zhwd-wwo

## Assignments
| Task 1 — Simple Math Word Problems | Pavithra | Raj | Venkat | Dnyeshwari
# | Task Measure | Model # Think 1 | Model # Think 2 | Model # Instruct 1 | Model # Instruct 2 | Comments
1 | Accuracy
2 | Response_Time
3 | Answer Quality
4 | Reasoning Quality (Thinking Models only)
5 | Cost per Query
| Task 2 — Simple Coding Questions | Pavithra | Raj | Venkat | Dnyeshwari
# | Task Measure | Model # Think 1 | Model # Think 2 | Model # Instruct 1 | Model # Instruct 2 | Comments
1 | Accuracy
2 | Response_Time
3 | Answer Quality
4 | Reasoning Quality (Thinking Models only)
5 | Cost per Query
| Task 3 — General Knowledge Q&A | Pavithra | Raj | Venkat | Dnyeshwari
# | Task Measure | Model # Think 1 | Model # Think 2 | Model # Instruct 1 | Model # Instruct 2 | Comments
1 | Accuracy
2 | Response_Time
3 | Answer Quality
4 | Reasoning Quality (Thinking Models only)
5 | Cost per Query

## Scorecard
# | Task Measure | Model # Think 1 | Model # Think 2 | Model # Instruct 1 | Model # Instruct 2 | Comments
1 | Accuracy
2 | Response_Time
3 | Answer Quality
4 | Reasoning Quality (Thinking Models only)
5 | Cost per Query

## Queries_log
# | Description | Status | Comments
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18

## Tasks_Dtls
1. What Is This Project About?
In this project, you will compare two types of AI models to understand how they think and respond differently:
• Thinking Models — These models "think out loud" before giving an answer. They reason through the problem step by step, similar to how a student solves a math problem by showing their work.
• Instruct Models — These models directly answer your question without showing any reasoning steps. They are fast, clear, and follow instructions well.
Your goal is to test both types of models on simple everyday tasks, compare their answers, measure how fast they respond, and decide when to use each type.
💡 Think of it this way: a Thinking Model is like a student who writes down all their calculation steps, while an Instruct Model is like a student who just writes the final answer.
4. Tasks You Will Test
You will test all 4 models on the same 3 types of tasks. Use the datasets or question sets listed below — they are beginner-friendly and freely available.
Task 1 — Simple Math Word Problems
• Dataset: GSM8K (Grade School Math) — 200 sample questions
• Example question: "Maria has 5 apples. She gives 2 to her friend and buys 3 more. How many does she have?"
• What to check: Did the model get the right answer? Did the thinking model show correct steps?
💡 GSM8K is free and available on Hugging Face: datasets/gsm8k
Task 2 — Simple Coding Questions
• Dataset: HumanEval (first 50 problems only) — beginner Python functions
• Example task: "Write a Python function that checks if a number is even or odd."
• What to check: Does the code run without errors? Does it give the correct output?
💡 You do not need to run code yourself — paste the model's output into an online Python runner like repl.it or Google Colab.
Task 3 — General Knowledge Q&A
• Dataset: TriviaQA (100 sample questions) or create your own 50-question set
• Example question: "What is the capital of Japan?" or "Explain how a vaccine works in simple words."
• What to check: Is the answer correct? Is the explanation clear and easy to understand?

## Models
2. Models You Will Use
You will work with 4 models — 2 Thinking Models and 2 Instruct Models. All of these can be accessed online for free or at very low cost.
Thinking Models (show their reasoning)
Model Name | Who Made It | What Makes It Special
DeepSeek-R1 (free) | DeepSeek AI | Free to use; shows all its reasoning steps; great for math and logic problems
o3-mini (OpenAI) | OpenAI | Compact and affordable; you can control how much it "thinks" (low / medium / high effort)
Instruct Models (answer directly)
Model Name | Who Made It | What Makes It Special
GPT-4o mini | OpenAI | Fast, cheap, and very reliable; great for everyday question-answering and writing tasks
Llama-3.1 8B Instruct | Meta AI (free) | Completely free and open source; can be run locally; good general-purpose assistant
💡 You can access DeepSeek-R1 free at chat.deepseek.com or via the DeepSeek API. Llama-3.1 8B is available free on Together AI and Groq.
3. The Key Difference — Explained Simply
| Thinking Model | Instruct Model
How it responds | First thinks step-by-step, then gives the final answer | Directly gives the final answer without showing steps
Speed | Slower — takes more time because it reasons first | Faster — answers almost immediately
Best for | Hard problems that need careful reasoning (math, logic, planning) | Simple and conversational tasks (Q&A, writing, summaries)
Cost | Uses more tokens (= slightly more expensive per query) | Uses fewer tokens (= cheaper per query)
Visible reasoning? | Yes — you can read how the model thought through the problem | No — only the final answer is shown
Think 1 | a) qwen/qwen3-32b GPT OSS 120 B
Think 2 | b) Open Ai O3 mini
--========
Instruct 1 | c) Llama-3.1 8B Instruct
Instruct 2 | d) Llama-3.3 70B versatile

## Contacts
Names | Mail Id | Contact Number
Group 1
RAJASEKHAR REDDY PALAVALI | rajshred@gmail.com | 7799945999
JIDIGAM VENKATA SAI PAVAN KALYAN | vspkalyan92@gmail.com | 8499967287
Dnyaneshwari Jayawant Shinde | sdnyaneshwari1@gmail.com | 7058528990
Ankit tiwari | ankitaamoriya@gmail.com | 7906871427
Pavithra PN | pavithrapn1935@gmail.com | 8762821935
Group 2
SOGALA RAHUL | rahulbaba.king8@gmail.com | 9666051295
Sahana G | gsahanaa99@gmail.com | 9611816843
Prasanna Nagarale | nagaraleprasanna@gmail.com | 9448178417
Santhosh Kumar H N | santhoshhn021@gmail.com | 9036272894
Vimal PM | vimalpm616@gmail.com | 9526614516
Group 3
Priyanka Samir Salve | priyanka.dsakat@gmail.com | 9970260276
kommahrushikeshwarreddy | kommahrushikeshwarreddy@gmail.com | 9154473254
Sneha Pramanik | snehapramanik2005@gmail.com | 79031 45552
Kapil Amarsing Patil | patilkapil241@gmail.com | 6351079183
Regards,
B Harish
8123416947
harish.b@excelr.com
Projects Management Team
Google - Meet Link for Group 1 | https://meet.google.com/edw-zhwd-wwo